GREEN TECH ELECTRIC

Construction Suite — Field Crew Quick Start

This is your one-page guide to logging the day's work in Odoo. Do these in order, every shift. If in doubt, save as a draft and ask your foreman — it's better to record something than nothing.

Signing in

- On a computer: open odoo.greentechelectric.ca and sign in with your Green Tech email and password.

- On your phone: open the same address in your browser (or the Odoo mobile app) and sign in. Add it to your home screen for one-tap access.

- Open the Construction app, then the Field & Safety menu — everything you need is there.

Your daily routine

1   Safety first — Toolbox Talk / FLHA

- Record the toolbox talk and your Field-Level Hazard Assessment before work starts. List the crew and the hazards you discussed.

2   Daily Site Log — the core of your day

- Create a new Daily Site Log for your project and today's date.

- Add a labour line for each worker: name, classification and hours.

- Fill in Work Completed, Quantities Installed, weather, deliveries, visitors and any delays.

- Attach photos of the work (before/after, deliveries, issues).

- Sign at the bottom, then Submit for your supervisor's review. A submitted log can't be edited — so check it first.

3   Field Issues — report a problem

- Hit a problem (access, damage, conflict, missing info)? Log a Field Issue with a photo and a short description so it's tracked and actioned.

4   Delays — log lost time

- If something cost you time, add a Delay Event: the cause, how many days, and whether it's on the critical path. This protects the schedule and any claim.

What you can view (read-only)

- Site Instructions issued to the crew — read and follow them; acknowledgement is recorded by the office.

- RFIs and drawings for your project — for reference. You won't see budgets or billing; that's office-only.

Photos & signatures — tips

- Take photos in good light and get the whole area in frame. More photos is better than fewer.

- Use your finger or a stylus to sign on the phone screen. If it looks wrong, clear and redo before submitting.

Equipment & permits

- Scan the QR code on a permit or piece of equipment to open its record and check it's current before use.

If something goes wrong

- No signal: the web page needs a connection. Note the details on paper and enter them when you're back in coverage — or ask the office about the Odoo mobile app for spotty sites.

- Submitted the wrong log: don't create a duplicate. Ask your foreman or PM — they can reopen it.

- Can't find a menu or a project: you may not be assigned to it yet. Ask your PM to add you.

Questions? Talk to your foreman or project manager. Green Tech Electric — Construction Suite.